## Slide 1
Banque Saudi Fransi
Onboarding Working Group Meeting
Instant Payment System
19th May 2020

## Slide 2
Contents
BSF | IPS
| 1
Introduction
High Level Project Plan
Risks
Issues
Dependencies
Assumptions
Question & Answers
IPS Working Group Meeting | Agenda

## Slide 3
IPS Working Group Meeting | BSF Plan
High Level Project Plan
| 6
Milestones | Completion Percent(Last Meeting) | Completion Percent(Current Status) | Completion Date(Baseline) | Completion Date(Actual)
Production environment Infrastructure readiness | 80% | 90% | Mar-20 | Apr-20
Solution Design | 100% | 100% | Feb-20 | Feb-20
Messages Implementation | 80% | 90% | Mar-20 | May-20
Central Profile Database Implementation Progress | 15% | 20% | Apr-20 | May-20
Configuration / Development / Customization of Payment Hub | 40% | 50% | Jun-20 | Jul-20
Channel Scope Finalization | 60% | 100% | Jun–20 | Jul-20
Business Requirement For Channel | 60% | 100% | Jun-20 | Jul-20
Customer Journey Incorporation | 0% | 20% | Jun-20 | Jul-20
Integration between the payment Hub and the E Channel | 0% | 10% | Jun-20 | Jul-20
Test Plan preparation (Out Source to Specialized QA Company) | 20% | 30% | Mar-20 | Jul-20
Unit Testing – E2E & Simulator Setup | 20% | 30% | Jun-20 | Aug-20
SIT Testing | 0% | 0% | Jun-20 | Aug-20
UAT Testing | 0% | 0% | Sep-20 | Sep-20
SP Certification Process | 0% | 0% | Aug-20 | Aug-20
IPS Production Rollout | 0% | 0% | Oct-20 | Nov-20
IPS DR Rollout | 0% | 0% | Oct-20 | Nov-20

## Slide 4
IPS Working Group Meeting | BSF Important RAID Log
| 12
Risks
BSF | IPS
Risk 1
Pending Documents
Mitigation - We have highlighted this point in our previous meeting with Saudi Payments and awaiting for the documents.
Risk 2
COVID 19 - Although mitigated earlier, unprecedented scenarios are taken into account
Mitigation – We are constantly monitoring the situation and keeping the resources in high state of cautiousness

## Slide 5
IPS Working Group Meeting | BSF Important RAID Log
| 12
Issues
BSF | IPS
To publish consumer data to Saudi Payments Central Consumer Database, a compliance agreement is required. The issue was raised on 14th April 2020 and the issue resolving due date is 31st May 2020
Mitigation – We are closely working with our compliance team to get the sign off on the agreement by end of May 2020
The CPDB scenarios related to registration, lookup and the workflows are being evaluated with respect to the bank’s risk appetite and against the SAMA recommendations and the same are being discussed with the internal risk team.
Scenario 1 - OTP Sending Mechanism
Mitigation – We are working closing with the compliance team, we are anticipating to resolve by end of May 2020
Scenario 2 - Defaulting of the IDS
Mitigation – We are working closing with the compliance team, we are anticipating to resolve by end of May 2020

## Slide 6
IPS Working Group Meeting | BSF Important RAID Log
| 12
Issues
BSF | IPS
There are chances for the fraud related to proxy registration which is very sensitive
Mitigation – We are working with our business team on validation of the ids to protect the interests of the customer
To register a proxy with an international number
Mitigation – We are working with the business team on how to be compliant on this with the SAMA guidelines

## Slide 7
IPS Working Group Meeting | BSF Important RAID Log
| 12
Dependancies
BSF | IPS
Documents expected on Pricing and Operational Rules in order to finalize the scope of the implementation from business perspective
Watch - We are awaiting for the response
Procurement of HSM Device.
Mitigation - We are acquiring the HSM device by matching the criteria and standards as per SAMA.
We are expecting and awaiting for the plan of Saudi Payments regarding the milestones and dates regards to that of IPS.
Watch – We have highlighted this to Saudi Payments and awaiting the response

## Slide 8
IPS Working Group Meeting | BSF Important RAID Log
| 12
Assumptions
BSF | IPS
BSF is expecting a simulator from Saudi Payment to execute Business Test Cases between August 2020 to September 2020
Accept – This was highlighted in the previous meeting and Saudi Payments has accepted to provide the same by June
BSF is expecting Test Cases for the certification process
Accept - This was highlighted in the previous meeting and Saudi Payments has accepted to provide the same by June
BSF is assuming that Saudi Payments have consulted with SAMA on enabling the right click for copy and paste of the proxy values and IBAN which is quiet vulnerable.
Watch – We are awaiting for the response

## Slide 9
Questions and Answers